|  |  |  |
| --- | --- | --- |
| **Client** |  *CRC Team* | *Meeting or Status Date: 6-7-18* |
| **Project** | *2018 FLU/ FIT Webinar Planning* | *Created By: Amber* |
| **Distribution** | *Sara, Emily, Coutney, Ginger,*  |  |

|  |
| --- |
| **Project Goals & Scope - Overview** |
| * *Reach 80% CRC screening rates by end of 2018*
* *Develop and strengthen partnerships across multiple stakeholders in MT*
 |

|  |
| --- |
| **Project Status - Summary** |
| Webinar Series: FLU/FIT FRIDAY’sEach webinar will consist of a “factual” discussion to be followed up with a “Facility Spotlight.” The Facility Spotlight will cover the following topic areas: What is your Why, What was your biggest challenge and how did you overcome it, What were your results, What are your needs/ plans for sustainability?Webinar 1: Aug 17th ACS and KRMC are speakers* ACS to complete the following review points
	+ Review of current data on CRC screening rates
	+ Review of new ACS screening standards
	+ Brief review of Flu/ FIT intervention for those that are new – encourage newcomers to visit older webinars for more info or post websites in chat
	+ Discussion of FIT test cost and efficacy
* Facility spotlight
 |
| Webinar 2: Sept 5th Amber and GFC are speakers* Reinforce staff training and workflow options
* Review ordering materials online
* Facility spotlight
 |
| Webinar 3: Sept 28th Promoting Internal Leadership with American Indian Focus: Molly/ Emily (?) and Partnership and Missoula Urban Indian Center are speakers* Review the importance of physician engagement and specific steps can a staff champion for successful program implementation
* Evaluating the effectiveness of FLU/FIT program
* Discuss early recognition of CRC
* Facility spotlight
 |
| Webinar 4: Oct 19th: Program Alignment and Payer Panel* Amber to present Quality Payment Program alignment/ Courtney to discuss UDS
* Payer panel: each payer will get 10 minutes to discuss their approach/ support of Health Promotion strategies, payer implications of new screening rates, promotion of FIT over colonoscopy as low cost intervention and other topics of their choice
* No facility spotlight
 |

|  |  |
| --- | --- |
| **Upcoming Events/Milestones**  | ***Comments*** |
|  |  |
|  |  |
|  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Action Items or Open Issues from Meeting**  | **Due Date:** | **Assigned To:** | ***Comments*** |
| Emily to contact Dr. Brooks or other ACS medical staff for presentation on this date | 6-30-18 | Emily |  |
| Create Survey Monkey for needs assessment for the group. Emily stated she may have one already we can re-purpose. Group needs to decide if we should poll during the webinar(s) or send out prior to event | 6-30-15 | Emily |  |
| Save the dates created for all events to be emailed out to all groups | 7-15-18 | Amber |  |
| See above for tentative presentation dates for Facilities. Obtain permission and date reservation for each | 7-15-18 | ALL | Courtney- GFCAmber- AllegianceMolly- KRMCEmily – Partnership and MUICAmber to invite Alona and/or Katelin |

|  |  |
| --- | --- |
| **Longer Term Issues/tasks** | ***Comments*** |
|  |  |
|  |  |
|  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Project Decisions - Overview** | **Date** | **Made By:** | ***Comments*** |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |